## Updates
District Formation |  | V1.0
Background and Usage
GNAT Bar Chart - Residential Development and Construction Timeline Line
Disclosure: The following timeline represents an estimated sequence for the design-through-construction process. Actual project schedules may vary depending on jurisdictional requirements, site conditions, topography, project size, and project type. This framework is intended to provide a baseline process to support organization, tracking, and management, particularly for both new and experienced project managers.
Version
V1.0 | 2025-12-13
Update of timeline and correction of bar chart color and spacing
Deleted Original Bar Charts, Created Simple GNAT Bar Chart
Beta: | 2012-06-01
Creationg of Planning and Construction Timeline
Use of Previous Single Family Home Develompment
Inputs and Detail - TABS BLUE
Disclaimer: The information provided is for planning and informational purposes only and does not constitute a guarantee of schedule, cost, or project outcomes. District Formation assumes no responsibility for variations resulting from regulatory approvals, site conditions, third-party actions, or unforeseen circumstances. Final schedules and deliverables are subject to applicable agreements, approvals, and project-specific conditions.

## Planning
Estimated Construction Timeline
Project Location : | [Property Address
Today Date: | 2025-12-13
Acquisition Date | 2025-12-13
Start Date | 2025-01-15
Task |  | Start Date | Duration Days | End Date | NOTES:
PLANNING |  | 2025-12-13 | 165 | 2026-05-27
Initial Development |  | 2025-12-13 | 30 | 2026-01-12
Land Survey |  | 2025-12-13 | 1 | 2025-12-14
Geological Test |  | 2025-12-13 | 1 | 2025-12-14
Percolation Test |  | 2025-12-13 | 1 | 2025-12-14
Program |  | 2025-12-13 | 1 | 2025-12-14
Architecture |  | 2026-01-12 | 60 | 2026-03-13
Conceptual Desgin |  | 2026-01-27 | 30 | 2026-02-26 | *3 Weeks
Schematic Design |  | 2026-02-11 | 1 | 2026-02-12 | *3 Weeks
Design Development |  | 2026-02-26 | 1 | 2026-02-27 | *1 Week
Construction Drawings |  | 2026-03-13 | 1 | 2026-03-14
Landscape |  | 2026-01-27 | 45 | 2026-03-13 | *2 Weeks After Arch
Civil Engineering |  | 2026-01-27 | 45 | 2026-03-13
HOA Submittal |  | 2026-03-13 | 0 | 2026-03-13 | *Can Remove If no HOA
Corrections |  | 2026-03-13 | 0 | 2026-03-13
HOA Submittal #2 |  | 2026-03-13 | 0 | 2026-03-13
Planning Submittal #1 |  | 2026-03-13 | 30 | 2026-04-12
Corrections |  | 2026-04-12 | 15 | 2026-04-27
Planning Submittal #2 |  | 2026-04-27 | 30 | 2026-05-27
BUILDING AND SAFETY |  | 2026-04-27 | 120 | 2026-08-25
Structure |  | 2026-04-27 | 45 | 2026-06-11
Prelminary
Framing
Retaining Wall
MEP |  | 2026-04-27 | 45 | 2026-06-11
Title 24
Civil and Landscape |  | 2026-04-27 | 45 | 2026-06-11
Fire Department Approval
Fuel Modification Approval
Interior Design |  | 2026-04-27 | 120 | 2026-08-25
Submittal #1 |  | 2026-06-11 | 30 | 2026-07-11 | *Action Linked to Completion of Structure
Corrections |  | 2026-07-11 | 15 | 2026-07-26
Submittal #2 |  | 2026-07-26 | 30 | 2026-08-25
Inspection - Drywall |  | #REF! | 1 | #REF!
GENERAL CONTRACTOR |  | 2026-07-11 | 120 | 2026-11-08
Start Sending Bids |  | 2026-07-11 | 45 | 2026-08-25 | *Linked to First Submittal
Inspection - Stucco |  | 2026-08-25 | 1 | 2026-08-26
Review |  | 2026-08-25 | 15 | 2026-09-09
Bid Set 2 |  | 2026-09-09 | 30 | 2026-10-09
Contract |  | 2026-10-09 | 30 | 2026-11-08
Construction Prep
BANKING |  | 2026-08-25 | 90 | 2026-11-23
Engage Banks |  | 2026-08-25 | 30 | 2026-09-24
Appraisal |  | 2026-09-24 | 15 | 2026-10-09
Loan Documents |  | 2026-09-24 | 60 | 2026-11-23
Fund Control |  | 2026-10-09 | 45 | 2026-11-23 | *Fund Control 2 Wks after Bank Initial Study
Insurance |  | 2026-10-09 | 45 | 2026-11-23
PERMITTING |  | 2026-11-08 | 30 | 2026-12-08
Surety Bond |  | 2026-11-08 | 30 | 2026-12-08
Grading |  | 2026-11-08 | 30 | 2026-12-08
Building |  | 2026-11-08 | 30 | 2026-12-08
Landscape |  | 2026-11-08 | 30 | 2026-12-08
Retaining |  | 2026-11-08 | 30 | 2026-12-08
Inspection - Final |  | #REF! | 1 | #REF!
Total Development Timeline |  | 2025-12-13 | 345 | 2026-11-23
Potential Studies
Land Survey
Geological Study
Percolation Test
Story Poles
Approvals
Fire Department
Health Department
Formulas:
Start Date = [Start Date, row above]
Start Date = [Start Date, row above]+15
End Date = [Start Date]+[Duration Days]
End Date = [Duration Days]+[Start Date]

## Construction
Estimated Construction Timeline
Project Location : | [Property Address
Today Date: | 2025-12-13
PreConstruction | 2026-12-08
Construction Start Date: | 2027-02-28
Task | Start Date | Duration Days | End Date | Notes
PHASE 1 (PRECONSTRUCTION) | 2026-12-08 | 60 | 2027-02-06
Misc (EC, Asbestos) | 2026-12-08 | 15 | 2026-12-23
DIG | 2026-12-23 | 15 | 2027-01-07
Utilities and Temp Facilities | 2026-12-23 | 15 | 2027-01-07
Demo | 2027-01-07 | 15 | 2027-01-22
Property Corners | 2027-01-22 | 15 | 2027-02-06
Grading | 2027-01-22 | 15 | 2027-02-06
Inspection Soils Compaction | 2027-02-03 | 1 | 2027-02-04 | Inspection
PHASE 2 (GROUND UP CONSTRUCTION) | 2027-02-06 | 166 | 2027-07-22
Trenching | 2027-02-06 | 15 | 2027-02-21
Underground Plumbing/Electrical | 2027-02-06 | 15 | 2027-02-21
Steel Frame | 2017-09-30 | 15 | 2017-10-15
Inspection - Rebar/Sewer/Electrical/Steel | 2027-02-21 | 1 | 2027-02-22
Concrete | 2027-02-21 | 30 | 2027-03-23
Rough Framing | 2027-03-23 | 60 | 2027-05-22 | *Linked to Concrete Completion
Inspection - Bolts/Hold Downs/ Strips | 2027-04-07 | 1 | 2027-04-08 | *Rough Framing Plus 15
Inspection- Floor/Slab/Steel | 2027-04-07 | 1 | 2027-04-08
Inspection - 1st/2nd/ roof sheating | 2027-04-07 | 1 | 2027-04-08 | *Rough Framing (+14)
Inspection - Frame/Bracing | 2027-04-07 | 1 | 2027-04-08 | *Rough Framing (+14)
Inspection- Weather Strip | 2027-04-07 | 1 | 2027-04-08 | *Rough Framing (+14)
Rough Mechanicals | 2027-04-07 | 45 | 2027-05-22 | *Rough Framing(15+)
Rough Elevator | 2027-04-07 | 1 | 2027-04-08
Rough Plumbing | 2027-04-07 | 1 | 2027-04-08
Rough Electircal | 2027-04-07 | 1 | 2027-04-08
Rough Fire Sprinklers | 2027-04-07 | 1 | 2027-04-08
Rough HVAC | 2027-04-07 | 1 | 2027-04-08
Rough Structural Steel | 2027-04-07 | 1 | 2027-04-08
Rough Low Voltage | 2027-04-07 | 1 | 2027-04-08
Fire Place | 2027-04-07 | 1 | 2027-04-08
Windows and Doors | 2027-04-07 | 45 | 2027-05-22
Inspection - Combo | 2027-05-22 | 1 | 2027-05-23
Insulation | 2027-05-23 | 15 | 2027-06-07
Inspection - Insulation | 2027-06-07 | 1 | 2027-06-08
Waterproofing | 2027-05-23 | 15 | 2027-06-07
Inspection - Drainage | 2027-06-07 | 1 | 2027-06-08
Roof Stock | 2027-05-23 | 15 | 2027-06-07
Drywall | 2027-06-07 | 45 | 2027-07-22 | *Done after Roofint Stock
Inspection - Drywall | 2027-07-22 | 1 | 2027-07-23
PHASE 3 (SHELL CONSTRUCTION) | 2027-07-22 | 90 | 2027-10-20
Stucco | 2027-07-22 | 45 | 2027-09-05 | *Estimated 45 days
Inspection - Stucco | 2027-09-05 | 1 | 2027-09-06
Stone Veneer | 2027-09-05 | 15 | 2027-09-20 | *Starts when Scaffold goes up
Gutters and Sheet Metal | 2027-09-05 | 15 | 2027-09-20 | *After Stucco Finishes
Inspection - Drainage | 2027-09-20 | 1 | 2027-09-21
Roofing | 2027-09-05 | 15 | 2027-09-20
Gypcrete | 2027-09-05 | 15 | 2027-09-20
Finished Carpentry | 2027-09-20 | 15 | 2027-10-05
Finished Elevator | 2027-09-20 | 15 | 2027-10-05
Painting | 2027-10-05 | 15 | 2027-10-20
PHASE 4 (FINISH) | 2027-10-20 | 75 | 2028-01-03
Tile | 2027-10-20 | 30 | 2027-11-19
Wrought Iron | 2027-11-04 | 15 | 2027-11-19 | *Starts half way of tile work
Cabinets | 2027-11-04 | 15 | 2027-11-19
CounterTops | 2027-11-19 | 15 | 2027-12-04
Finish Mechanical | 2027-12-04 | 15 | 2027-12-19
Plumbing Finishes | 2027-12-04 | 15 | 2027-12-19
Electrical Finishes | 2027-12-04 | 15 | 2027-12-19
Low Voltage Finish | 2027-12-04 | 15 | 2027-12-19
HVAC Finishes | 2027-12-04 | 15 | 2027-12-19
Fire Sprinkler Finishes | 2027-12-04 | 15 | 2027-12-19
Alarm Finishes | 2027-12-04 | 15 | 2027-12-19
Inspection- Fire Sprinkler | 2027-12-19 | 1 | 2027-12-20
Shower Drains/Mirrors | 2027-12-19 | 15 | 2028-01-03
Hardware | 2027-12-19 | 15 | 2028-01-03
Wood Flooring | 2027-12-19 | 15 | 2028-01-03
Carpets | 2027-12-19 | 15 | 2028-01-03
Inspection- Planning Inspection | 2028-01-03 | 1 | 2028-01-04
PHASE 5 (ON-SITE CONSTRUCTION) | 2028-01-03 | 12 | 2028-01-15
Finish Grading | 2028-01-03 | 15 | 2028-01-18
Pool | 2028-01-03 | 30 | 2028-02-02
Offsite Work | 2028-01-03 | 30 | 2028-02-02
Driveway | 2028-01-03 | 10 | 2028-01-13
Gate | 2028-01-03 | 10 | 2028-01-13
Fencing | 2028-01-03 | 10 | 2028-01-13
Landscape | 2028-01-03 | 10 | 2028-01-13
Pick-Up Work | 2028-01-13 | 45 | 2028-02-27
Clean Up | 2028-01-13 | 1 | 2028-01-14
Inspection - Final | 2028-01-14 | 1 | 2028-01-15
Total Construction Time | 2026-12-08 | 402 | 2028-01-14
Stage One Ordering
Plmbing Fixtures | 2027-02-06 |  |  |  | CONCRETE | ES= | EARLIER START
Electrical Rough | 2027-02-06 |  |  |  | FRAMING | EF | EARLY FINISH
Roof Truss | 2027-02-06 |  |  |  | PLUMBING | LF | LATE FINISH
Lumber | 2027-02-06 |  |  |  | ELECTRICAL | LS | LATE START
Steel | 2027-02-06 |  |  |  | HVAC
Fire Sprinklers | 2027-02-06 |  |  |  | INTERIOR
Roof Tiles | 2027-02-06 |  |  |  | roofing
Windows | 2027-02-06 |  |  |  | FINISHED CARPENTDER
Precast | 2027-02-06
Waterproofing | 2027-02-06
Stage Two Ordering
Formulas:
Start Date = [End Date, row above]
Start Date = [Start Date, row above]
End Date = [Start Date]+[Duration Days]
End Date = [Duration Days]+[Start Date]

## Printable
Note: Adjust Chart Date by Clicking Date Series on Chart --> Format Axis --> Axis Option (Last Option Histogram Bar Icon) -->Bounds - 'Minimum' and 'Maximum' Amounts --> "Start Date" and "End Date"
Planning Phase Timeline
Task | Start Date | End Date | Duration (Days)
Planning
Initial Development | 2025-12-13 | 2026-01-12 | 30
Architecture | 2026-01-12 | 2026-03-13 | 60
Landscape | 2026-01-27 | 2026-03-13 | 45
Civil Engineering | 2026-01-27 | 2026-03-13 | 45
Approval Time | 2026-03-13 | 2026-05-27 | 75
Building and Safety
Structure | 2026-04-27 | 2026-06-11 | 45
MEP | 2026-04-27 | 2026-06-11 | 45
Title 24 | 2026-04-27 | 0 | 0
Civil and Landscape | 2026-04-27 | 2026-06-11 | 45
Interior Design | 2026-04-27 | 2026-08-25 | 120
Approval Time | 2026-06-11 | 2026-08-25 | 75
General Contractor
Start Sending Bids | 2026-07-11 | 2026-08-25 | 45
Review | 2026-08-25 | 2026-08-26 | 15
Bid Set 2 | 2026-09-09 | 2026-09-09 | 30
Contract | 2026-10-09 | 2026-10-09 | 30
Banking
Engage Banks | 2026-08-25 | 2026-09-24 | 30
Appraisal | 2026-09-24 | 2026-10-09 | 15
Loan Documents | 2026-09-24 | 2026-11-23 | 60
Permitting
Surety Bond | 2026-11-08 | 2026-12-08 | 30
Grading | 2026-11-08 | 2026-12-08 | 30
Building | 2026-11-08 | 2026-12-08 | 30
Landscape | 2026-11-08 | 2026-12-08 | 30
Retaining | 2026-11-08 | 2026-12-08 | 30
Construction Phase Timeline
Task | Start Date | End Date | Duration (Days)
PHASE 1 (SITE PREP)
Misc (EC, Asbestos) | 2026-12-08 | 2026-12-23 | 15
DIG | 2026-12-23 | 2027-01-07 | 15
Utilities and Temp Facilities | 2026-12-23 | 2027-01-07 | 15
Demo | 2027-01-07 | 2027-01-22 | 15
Property Corners | 2027-01-22 | 2027-02-06 | 15
Grading | 2027-01-22 | 2027-02-06 | 15
PHASE 2 (GROUND UP CONSTRUCTION)
Trenching | 2027-02-06 | 2027-02-21 | 15
Underground Plumbing/Electrical | 2027-02-06 | 2027-02-21 | 15
Steel Frame | 2017-09-30 | 2017-10-15 | 15
Concrete | 2027-02-21 | 2027-03-23 | 30
Rough Framing | 2027-03-23 | 2027-05-22 | 60
Rough Mechanicals | 2027-04-07 | 2027-05-22 | 45
Fire Place | 2027-04-07 | 2027-04-08 | 1
Windows and Doors | 2027-04-07 | 2027-05-22 | 45
Insulation | 2027-05-23 | 2027-06-07 | 15
Waterproofing | 2027-05-23 | 2027-06-07 | 15
Roof Stock | 2027-05-23 | 2027-06-07 | 15
Drywall | 2027-06-07 | 2027-07-22 | 45
PHASE 3 (SHELL CONSTRUCTION)
Stucco | 2027-07-22 | 2027-09-05 | 45
Stone Veneer | 2027-09-05 | 2027-09-20 | 15
Gutters and Sheet Metal | 2027-09-05 | 2027-09-20 | 15
Roofing | 2027-09-05 | 2027-09-20 | 15
Gypcrete | 2027-09-05 | 2027-09-20 | 15
Finished Carpentry | 2027-09-20 | 2027-10-05 | 15
Finished Elevator | 2027-09-20 | 2027-10-05 | 15
Painting | 2027-10-05 | 2027-10-20 | 15
PHASE 4 (FINISH)
Tile | 2027-10-20 | 2027-11-19 | 30
Wrought Iron | 2027-11-04 | 2027-11-19 | 15
Cabinets | 2027-11-04 | 2027-11-19 | 15
CounterTops | 2027-11-19 | 2027-12-04 | 15
Finish Mechanical | 2027-12-04 | 2027-12-19 | 15
Shower Drains/Mirrors | 2027-12-19 | 2028-01-03 | 15
Hardware | 2027-12-19 | 2028-01-03 | 15
Wood Flooring | 2027-12-19 | 2028-01-03 | 15
Carpets | 2027-12-19 | 2028-01-03 | 15
PHASE 5 (ON-SITE CONSTRUCTION)
Finish Grading | 2028-01-03 | 2028-01-18 | 15
Pool | 2028-01-03 | 2028-02-02 | 30
Offsite Work | 2028-01-03 | 2028-02-02 | 30
Driveway | 2028-01-03 | 2028-01-13 | 10
Gate | 2028-01-03 | 2028-01-13 | 10
Fencing | 2028-01-03 | 2028-01-13 | 10
Landscape | 2028-01-03 | 2028-01-13 | 10
Pick-Up Work | 2028-01-13 | 2028-02-27 | 45
Clean Up | 2028-01-13 | 2028-01-14 | 1